## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
E01a | Verify User Identification | As a station manager I want to ask users to scan their campus id card So that I can varify user's identification | 2 | 2 | 1.Verify that user ID is 9 digits. 2.Verify that user exists in system matching details given | coder in duty: Boyang Zhang,Yaowen Hu
E01b | Verify user status | As a station manager I want to check user's current status So that I can provide permitted action for current user. | 3 | 2 | 1.Verify that user is renting or returning. 2.Verify that weather the user has uncleared fine. | coder in duty: Xiaojie Lv, Guang Yang
E02a | Check weather take the scooter | As a registered user I want to take a scooter after provide my id information. | 1 | 1 | 1.The slot won’t unlock untill the user status is varified 2.Varify that current station has a free scooter. | coder in duty: Xi liu, Beiming Yu
E02b | Check weather return the scooter | As a registered user I want to return the scooter to a slot to finish using. | 1 | 1 | 1.Make sure that the user is current using a scooter. 2.Make sure that the station has empty slots. 3.When finishi using a scooter, call the system to calculate usage. | coder in duty: Boyang Zhang,Yaowen Hu
E02c | Get light notification | As a user I want to get a light flashing notice. So that I can follow the light flashing to the slot | 3 | 3 | 1.The flashing light is on the right slot. 2.Flashing will stop when the scooter is taken or returned. | coder in duty: Xiaojie Lv, Guang Yang
E02d | Lock a slot | As a station manager I want to lock the slot if the scooter is taken or returned So that I can reuse the scooter and slot. | 1 | 1 | 1.Verify that the scooter was taken or returned successfully, then the slot is locked. | coder in duty: Xiaojie Lv, Guang Yang
E03a | Time-out unborrow | As a station manager I want to lock the slot if the scooter is not taken for one minute. So that other people can't take the scooter. | 2 | 2 | 1.Varify that the scooter was not taken for one minute. 2.Make sure that user's last action is not executed | coder in duty: Xi liu, Beiming Yu
E03b | Time-out unreturn | As a station manager I want to relock the empty slot if the user didn’t return a scooter for one minute. So that I can free the slot. | 2 | 2 | 1.Varify that the scooter was not returned for one minute. 2.Make sure that user's last action is not executed | coder in duty: Xi liu, Beiming Yu
E04a | Show slot's position | As a user I want the screen show me that which slot is unlocked for me. So that I can use that slot. | 2 | 2 | 1.Present the place of slot accurately 2.Make sure the screen display messages promptly to user during the operation. | coder in duty: Boyang Zhang,Yaowen Hu
E04b | Show current status | As a user I want the screen show me how long have I used the scooter. So that I can check my status. | 4 | 5 | 1.Show the user current time. 2.Make sure the user is noticed if the user action is limited 3.Make sure the interface is easy to use. | coder in duty: Xiaojie Lv, Guang Yang
E05a | User information obtain | As an administrator I want to obtain the relative information(QM number,full name,e-mail address) So that I can input it to system | 2 | 2 | 1.Make sure the QM number is in 9-bits 2.Make sure the e-mail address's format is XXX@xxx.com | coder in duty: Boyang Zhang,Yaowen Hu
E05b | Duplication check | As an administrator I want to verify if the information exists already, if not add the information into system So that complete the registration | 2 | 2 | 1.If the information exists, system should return a massage | coder in duty: Xiaojie Lv, Guang Yang
E06a | Calulate user's single time usage | As an administrator I want to get the return and borrowing time of a scooper and caluculate the time once a single scooper usage complement. So that I can know the time used | 3 | 3 | 1.System should return the time value caculated | coder in duty: Boyang Zhang,Yaowen Hu
E06b | Calulate user's usage of time in one day | As an administrator I want to add up each single time usage in one day every time when the scooper returned. So that I can get a have-used time in this day. | 3 | 3 | 1.System should return the time value caculated | coder in duty: Xiaojie Lv, Guang Yang
E06c | Overtime check for single usage | As an administrator I want to check the time usage for a single usage and determine if exists overtime,if exists, user will be fined 100 pounds. So that I can check the overtime for single usage and fine | 3 | 3 | 1.There exists overtime if usage of time exceed 30 minutes. | coder in duty: Boyang Zhang,Yaowen Hu
E06d | Overtime check for daily usage | As an administrator I want to check the time usage for a whole day and determine if exists overtime, once overtime, user will be fined 100 pounds. So that I can check overtime for daily and fine | 3 | 3 | 1.There exists overtime if usage of time exceed 2 hours | coder in duty: Xiaojie Lv, Guang Yang
E06e | Lock user | As an administrator I want to unable the user's borrowing authority if the user has been fined. So that suspend the user's account | 4 | 4 | 1.Make sure that a locked user can't get scooper in stations 2.User has been fined over 100 pounds should be locked. | coder in duty: Xi liu, Beiming Yu
E06g | receive fine paid by users | As an administrator I want to receive fine from users So that I can terminate of lock-in of use rights | 4 | 4 | 1.Check whether the user has paid a sufficient amount of fine | coder in duty: Xiaojie Lv, Guang Yang
E06h | Unlock User's Right of Use | As an administrator I want to unlock user's right for use After he had paid the fine So that I can I can allow users to continue using scooters | 4 | 5 | 1.Ensure that the user has paid a fine. 2.Make the user unlocked. | coder in duty: Boyang Zhang,Yaowen Hu
E07a | Check the usage of user | As an administrator I want to input the user ID to get the information from the User Database (TXT or XML) So that I can know any user’s usage. | 3 | 3 | 1.If the ID inputted by the admin is not exist, return a error code to tell Admin this ID no exist. | coder in duty: Xi liu, Beiming Yu
E07b | Send e-mail to any user about their weekly usage. | As an administrator I want to get all of usage of users, and then export them as text file. So that I can users can know about their usage by check their e-mail. | 3 | 3 | 1.Ask the user in advance if they need an e-mail reminder service and make a mark, and choose a stable time point (Like Saturday 8 .pm) to send e-mail weekly. | coder in duty: Boyang Zhang,Yaowen Hu
E07c | Monitor the status of each docking station about scooters that have not been used yet. | As an administrator I want to choose any docking station, and then get the information (How many scooters are currently available at each station ) about the docking station. So that if the station don't have enough scooters for the next user to use, managers need to manually add a number of new scooters to this station. | 3 | 3 | 1,System user friendly. 2, Additives for subsequent functions. | coder in duty: Xi liu, Beiming Yu
E07d | Monitor the status of each docking station about scooters being used | As an administrator I want to choose any docking station, and then get the information (How many scooters are currently in use.) about the docking station. So that if the station has more scootersbeing used than other station, the station must be expanded because it's on the main road. | 3 | 4 | 1.System user friendly. 2. Additives for subsequent functions. | coder in duty: Xi liu, Beiming Yu
E07e | Calculate user's usage time in a week | As an administrator I want to caculate all time usage for a user every day and save it to log So that I can know the user's weekly usage | 3 | 4 | 1.System do this at 23:59 every day 2.result should be output to log | coder in duty: Xi liu, Beiming Yu
E08 | Make the GUI | As an administrator I want to have a GUI So that easy to operate the system | 4 | 5 | 1.GUI should be user-friendly | coder in duty: Boyang Zhang,Yaowen Hu